## Sheet1
Research to topic |  | Durations | Stat Date | End Date
Phase 1: Planning and Requirement Analysis |  | 3 weeks | 13/092023 | 29/09/2023
Task 1: Research and project finalize |  | 5 day | 13/092023 | 18/09/2023
Task 1: Scrum planning |  | 5 day | 20/09/2023 | 25/09/2023
Task 2: Client meeting |  | 2 day | 26/09/2023 | 27/09/2023
Task 3: Requirement collection |  | 5 day | 28/09/2023 | 29/09/2023
Phase 2: Defining Requirements |  | 2 weeks | 2023-01-10 | 13/10/2023
Task 1: User stories |  | 6 day | 2023-01-10 | 2023-06-10
Task 2: Product Backlog |  | 6 day | 2023-08-10 | 13/10/2023
Phase 3: Designing the Project Architecture |  | 3 weeks | 15/10/2023 | 2023-10-11
Task 1: Usecase development, more… |  | 6 day | 15/10/2023 | 20/10/2023
Task 2: DFD, Stractural Chart, etc. |  | 6 day | 29/10/2023 | 2023-03-11
Task 3: Wireframe, UI/UX Design |  | 6 day | 2023-05-11 | 2023-10-11
Phase 4: Building or Developing the Project |  | 14 weeks | 20/11/2023 | 2024-01-03
Task 1: Backend development |  | 5 weeks | 20/11/2023 | 29/12/2024
Sprint 1: DBMS creation | Sprint Planning | 1 day | 20/11/2023 | 20/11/2023
| Sprint Backlog | 1 day | 21/11/2023 | 21/11/2023
| Development | 7 day | 22/11/2023 | 29/11/2023
| Testing | 2 day | 30/11/2023 | 2023-01-12
| Sprint Review, Retrospective and Release | 2 day | 2023-04-11 | 2023-05-12
Sprint 2: API development | Same process of Sprint 1 | 12 day | 2023-06-12 | 20/12/2023
Sprint 3: Web development with UI | Same process of Sprint 1 | 9 day | 21/12/2023 | 29/12/2024
Task 2: Frontend development |  | 9 weeks | 31/12/2023 | 2024-01-03
Sprint 4: Local database with CRUD and Retrofit to API call | Same process of Sprint 1 | 6 day | 31/12/2023 | 2024-05-01
Sprint 5: Mobile UI development | Same process of Sprint 1 | 12 day | 2024-07-01 | 19/01/2-24
Sprint 6: Authentication development | Same process of Sprint 1 | 6 day | 21/01/2024 | 26/01/2024
Sprint 7: Frontend and backent connection | Same process of Sprint 1 | 6 day | 28/01/2024 | 2024-02-02
Sprint 8: Google services implement | Same process of Sprint 1 | 12 day | 2024-04-02 | 16/02/2023
Sprint 9: Firebase implement | Same process of Sprint 1 | 12 day | 18/02/2024 | 2024-01-03
Phase 5: Testing |  | 2 weeks | 2024-03-03 | 15/03/2024
Task 1: White box test | (source code and design documents) | 5 day | 2024-03-03 | 2024-04-03
Task 2: Block Box Test | 2.1 Funcational Test (system work folw) | 5 day | 2024-05-03 | 2024-10-03
| 2.2 Non-Funcational Test (system performance) | 5 day | 2024-11-03 | 15/03/2024
Phase 5: Project Deployment |  | 3 weeks | 17/03/2024 | 2024-05-04
Test 1: Summarize the deployment project |  | 6 day | 17/03/2024 | 22/03/2024
Test 2: Document and mitigate risks |  | 12 day | 25/03/2024 | 2024-05-04
Phase 6: Maintenance |  | 1 weeks | 2024-01-04 | 2024-05-04
Task 1: Maintaint about the project level problem |  | 6 day | 2024-01-04 | 2024-05-04
April first week
Phase 7: Project Review and Release |  | 1 week | 2024-07-04 | 2024-12-04
Task 1: Project review and sumbit |  | 6 day | 2024-07-04 | 2024-12-04